## Risklist.csv
[6 empty] | Iteration |  | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9
ID | Task | Risks | Description | Countermeasure | Date | Type | IMP | PRB | MAG | PRB | MAG | PRB | MAG | PRB | MAG | PRB | MAG | PRB | MAG | PRB | MAG | PRB | MAG | PRB | MAG
1 | Team building and getting to know each other | Lack of team cohesion | Insufficient team bonding may lead to communication breakdowns and conflicts, hindering effective collaboration. | Conduct team-building activities early on | 2023-11-13 | Team Dynamic | 5 | 80% | 4 | 60% | 3 | 20% | 1 | 10% | 0.5 | 5% | 0.25 | 2% | 0.1 | 0 | 0 | 0 | 0 | 0 | 0
2 | Distribution of roles | Misalignment of skills and responsibilities | Inadequate alignment of team members' skills with roles may result in inefficiencies and hinder task completion. | Clearly define roles and responsibilities | 2023-11-13 | Resource Allocation | 4 | 70% | 2.8 | 50% | 2 | 25% | 1 | 20% | 0.8 | 7% | 0.28 | 5% | 0.2 | 0 | 0 | 0 | 0 | 0 | 0
3 | Agreement on a common working method | Differences in work preferences and styles | Divergent work preferences and styles may impede collaboration, affecting overall efficiency and work quality. | Establish a team agreement for working methods | 2023-11-13 | Team Dynamic | 3 | 60% | 1.8 | 30% | 0.9 | 15% | 0.45 | 10% | 0.3 | 5% | 0.15 | 2% | 0.06 | 0 | 0 | 0 | 0 | 0 | 0
4 | Getting to know the task | Incomplete understanding of the project scope | Team members not fully comprehending the project scope may lead to incorrect assumptions and incomplete work. | Conduct thorough project briefings and training | 2023-11-13 | Scope Definition | 5 | 80% | 4 | 50% | 2.5 | 10% | 0.5 | 5% | 0.25 | 2% | 0.1 | 2% | 0.1 | 0 | 0 | 0 | 0 | 0 | 0
5 | Contact and meeting with client | Difficulty in scheduling and coordinating meetings | Challenges in scheduling meetings with the client may cause delays in gathering essential project requirements. | Use scheduling tools and establish clear communication | 2023-11-20 | Communication | 4 |  | 0 | 80% | 3.2 | 40% | 1.6 | 20% | 0.8 | 5% | 0.2 | 2% | 0.08 | 0 | 0 | 0 | 0 | 0 | 0
6 | Contact and meeting with coach | Coach availability and communication challenges | Challenges in coach availability and communication may hinder guidance and support for the team. | Establish a communication schedule with the coach | 2023-11-20 | Stakeholder Engagement | 3 |  | 0 | 70% | 2.1 | 50% | 1.5 | 25% | 0.75 | 10% | 0.3 | 7% | 0.21 | 0 | 0 | 0 | 0 | 0 | 0
7 | Development and finalization of the vision | Lack of clarity in the project vision | Insufficient clarity in the project vision may lead to misunderstandings and divergent expectations. | Conduct thorough discussions to clarify the project vision | 2023-11-20 | Project Planning | 3 |  | 0 | 80% | 2.4 | 30% | 0.9 | 15% | 0.45 | 7% | 0.21 | 5% | 0.15 | 0 | 0 | 0 | 0 | 0 | 0
8 | Creation of a rough graphic prototype | Technical challenges in creating the prototype | Technical difficulties in creating the prototype may lead to delays and impact the demonstration of key functionalities. | Conduct a feasibility analysis for the chosen technology | 2023-11-27 | Technical | 4 |  | 0 |  | 0 | 80% | 3.2 | 50% | 2 | 10% | 0.4 | 5% | 0.2 | 0 | 0 | 0 | 0 | 0 | 0
9 | Workshop for all with Github | Limited understanding of Github among team members | Limited understanding of Github may hinder effective collaboration. | Provide Github tutorials and training sessions | 2023-11-28 | Tool Adoption | 3 |  | 0 |  | 0 | 70% | 2.1 | 60% | 1.8 | 20% | 0.6 | 10% | 0.3 | 0 | 0 | 0 | 0 | 0 | 0
10 | Creation of the use case model | Ambiguity in use-case requirements | Ambiguous use-case requirements may lead to misunderstandings and result in an inadequate use-case model. | Collaborate closely with stakeholders for clear requirements | 2023-11-30 | Requirements | 5 |  | 0 |  | 0 | 80% | 4 | 50% | 2.5 | 10% | 0.5 | 5% | 0.25 | 0 | 0 | 0 | 0 | 0 | 0
11 | Elaboration of UC01 | Lack of detailed information for UC01 | Insufficient detailed information for UC01 may lead to incomplete work and potential misalignment with stakeholder expectations. | Schedule sessions with domain experts for information gathering | 2023-12-01 | Requirements | 3 |  | 0 |  | 0 | 60% | 1.8 | 40% | 1.2 | 17% | 0.51 | 10% | 0.3 | 0 | 0 | 0 | 0 | 0 | 0
12 | Elaboration of UC03 | Misinterpretation of UC03 requirements | Misinterpretation of UC03 requirements may lead to incorrect use-case specifications and impact the overall project. | Establish regular communication channels with stakeholders | 2023-12-05 | Requirements | 4 |  | 0 |  | 0 | 70% | 2.8 | 30% | 1.2 | 15% | 0.6 | 10% | 0.4 | 0 | 0 | 0 | 0 | 0 | 0
13 | Further education for all with Github | Resistance to adopting Github as a collaboration tool | Resistance to Github adoption may hinder effective collaboration and version control. | Communicate the benefits of Github for collaboration and version control | 2023-12-11 | Tool Adoption | 3 |  | 0 |  | 0 | 80% | 2.4 | 50% | 1.5 | 20% | 0.6 | 5% | 0.15 | 0 | 0 | 0 | 0 | 0 | 0
14 | Workshop for developers and testers | Limited collaboration and understanding between developers and testers | Limited collaboration and understanding between developers and testers may result in inefficient testing processes. | Organize joint training sessions for developers and testers | 2023-12-11 | Team Dynamic | 4 |  | 0 |  | 0 |  | 0 | 60% | 2.4 | 15% | 0.6 | 10% | 0.4 | 0 | 0 | 0 | 0 | 0 | 0
15 | Preparation of the risk list | Overlooking potential project risks | Failure to identify potential risks may lead to inadequate risk management and project disruptions. | Engage the entire team in a collaborative risk identification session | 2023-12-11 | Project Planning | 3 |  | 0 |  | 0 |  | 0 | 80% | 2.4 | 30% | 0.9 | 20% | 0.6 | 0 | 0 | 0 | 0 | 0 | 0
16 | Frontend development | Errors in frontend development | Issues in frontend development may lead to a suboptimal user interface and user experience. | Have a backup plan with alternative frontend frameworks or approaches | 2023-12-18 | Technical | 5 |  | 0 |  | 0 |  | 0 | 80% | 4 | 10% | 0.5 | 10% | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
17 | Backend development | Errors in backend development | Issues in backend development may lead to system instability and performance issues. | Have a rollback plan and alternative backend solutions | 2023-12-18 | Technical | 5 |  | 0 |  | 0 |  | 0 | 80% | 4 | 20% | 1 | 10% | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
18 | Team member leaving the team | Unexpected departure of a team member | A team member leaving the team unexpectedly can disrupt the workflow and impact project knowledge and expertise. | Cross-train team members to mitigate the impact | 2023-12-20 | Team Dynamic | 5 |  | 0 |  | 0 |  | 0 |  | 0 | 90% | 4.5 | 60% | 3 | 0 | 0 | 0 | 0 | 0 | 0
19 | The role of the analyst must be taken on | Elimination analysts in the 2nd semester | Due to the fact that the industrial engineers are only at SE1, our last analyst at the moment will be omitted. | A team member must be entrusted with the analyst's tasks | 2024-01-22 | Team Dynamic | 5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 90% | 4.5 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Ø | 3.15 |  | 2.3 |  | 1.79 |  | 1.58 |  | 0.68 |  | 0.42 |  | #N/A |  | #N/A |  | #N/A